[Event planning template]

| Event concept and committee formation |  |
| --- | --- |
| Name of event |  |
| Date of event |  |
| Time of event |  |
| Location of event |  |
| Event coordinator/contact person |  |
| Target audience – who - Which group(s) is the event targeted attendee? - What does the audience need/want to know? - What will hold their interest? |  |
| Message – what - What do you want to say to the target audience? - What do you want them to know/do? |  |
| Objectives – why Be clear about what you hope to achieve with this event – actionable & measurable |  |
| Description of event – what |  |
| Risk assessment – what Identify possible risks and develop strategies to minimise risks |  |
| Evaluation criteria established - What were our aims/objectives? - Did we achieve what we set out to do? - Did it come in on budget? - What were the intended/unintended outcomes? - How do we measure effectiveness? - What tools do we use to measure our success? |  |
| Checklist  Who will be involved in organizing the event  Date/s of event determined  Location/venue for event booked  Target audience determined  Message determined  Objectives set  Risk assessment completed  Evaluation criteria established |  |

| Early event planning [12 – 6 months prior] | Person responsible |  |  | Action |  | Date to be completed |
| --- | --- | --- | --- | --- | --- | --- |
| Develop proposed program  Topics  Format  Potential leaders / speakers |  |  |  |  |  |  |
| Budget  Funding sources identified  Sponsorship  Estimate registration level  IEEE/Non-IEEE Break-even point established  Establish registration fees – IEEE/Non-IEEE  Create budget projections MCE Conference Business Operations can provide guidance, information, services and support for these steps |  |  |  |  |  |  |
| Overall event approvals – IEEE Unit approval  Sponsors  Budget  Patrons/Exhibitors IEEE review / approval  Contracts  Budget |  |  |  |  |  |  |
| Venue Selection  Create event specification and facility needs  Venue identification / negotiation  Contract development / review / approval  IEEE review and approvals MCE Event Management Services can provide guidance, services and support for these steps |  |  |  |  |  |  |
| Registration Management  Determine tool or method  Payment acceptance MCE Event Management Services can provide guidance, services and support for these steps |  |  |  |  |  |  |
| Exhibitor and Patron Plans  Define goals  Develop benefit packages and price  Target list  Marketing program  Space and equipment needs specified with venue MCE Event Management Services can provide guidance, services and support for these steps |  |  |  |  |  |  |
| Program Planning [9 months – 2 months prior] |  |  |  |  |  |  |
| Speakers  Identify several speaker candidates  Invitations  Confirm dates |  |  |  |  |  |  |
| Program/running sheet/speeches  Program finalised  Running sheet written  Program/running sheet sent to speakers  Speakers fully briefed  Opening, Closing and Housekeeping comments prepared  Let caterers know program - when to serve drinks/food |  |  |  |  |  |  |
| Marketing program [9 months – 1 month] |  |  |  |  |  |  |
| Advertising/Promotion  Website developed  eMarketing, Flyer, Social Media plans developed  Media release –Contact the Office of Communications MCE Event Management Services can provide guidance, services and support for these steps |  |  |  |  |  |  |
| Targeted attendee list  Past attendee/ prospect list generated/updated  Invitation composed  Invitation checked  Invitations sent MCE Event Management Services can provide guidance, services and support for these steps |  |  |  |  |  |  |
| Signage/Printed Materials  Organize as necessary  Verify brand consistency and compliance |  |  |  |  |  |  |
| Value added for guests  Copy of publication, CD-ROM  Gifts  Programs  Catalogues  Special offers/discounts  Competitions  Prizes |  |  |  |  |  |  |
| Event management [6 months – 1 month prior] | Person responsible |  |  | Action |  | Date to be completed |
| Space planning  Registration needs  Program needs  Furniture/other needs |  |  |  |  |  |  |
| Food and beverage (F&B)  Determine F&B needs  Service style  Menu choices  Special dietary requirements of guests MCE Event Management Services can provide guidance, services and support for these steps |  |  |  |  |  |  |
| Audio/visual requirements  PA system  video  Lapel or handheld microphone  Lighting  Extra electrical requirements  Lectern |  |  |  |  |  |  |
| Security  Event Disaster Plan created  Security alerted  Occupational health, welfare and safety concerns addressed  Provision of first aid |  |  |  |  |  |  |
| Speakers  Re-confirm dates  Confirm travel needs and dates  Audio-visual needs/preferences  Brief / Rehearsals  Bio/Introductory remarks |  |  |  |  |  |  |
| Onsite management [6 months – 1 month prior] | Person responsible |  |  | Action |  | Date to be completed |
| Registration Management  Onsite plan/staffing  Badges/lanyards MCE Event Management Services can provide guidance, services and support for these steps |  |  |  |  |  |  |
| Staffing  Extra required  Volunteers to meet and greet guests  Volunteer training materials and plans |  |  |  |  |  |  |
| Ambience  Intro presentation, static slides, housekeeping slides  Background music |  |  |  |  |  |  |
| Program/running sheet/speeches  Program finalised  Running sheet written  Program/running sheet sent to speakers  Speakers fully briefed  Opening, Closing and Housekeeping comments prepared  Let caterers know program - when to serve drinks/food |  |  |  |  |  |  |
| Guest comfort  Wheelchair access  Toilet facilities |  |  |  |  |  |  |
| Hospitality  Welcome signage at entrance  Ushers briefed  Cloak room  Red carpet |  |  |  |  |  |  |
| Housekeeping  Cleaning before and after  On standby during the event |  |  |  |  |  |  |
| Day of event planning |  |  | Person responsible |  | Action | Date to be completed |
| On the day  Time for set up by whom  Time for dismantle by whom  Dais, stage  Tables, chairs layout  Chair covers  Floor plan  VIP seating  Book courier/transport  Name tags  Clear location directions  Registration desk  Speaker Gifts  Exhibitor and Patron management |  |  |  |  |  |  |
| Post event planning [ 1-7 days after event] |  |  | Person responsible |  | Action | Date to be completed |
| After the event  Debrief  Comments on all aspects (negative and positive)  Guest / Speaker / Volunteer feedback  Guidelines for improvement next time  Evaluation against criteria  Celebration  Gratuities  Thank You’s – Exhibitors/Patrons, Volunteers, speakers and committee |  |  |  |  |  |  |